## Slide 1: T1 Works Request & Access Process
May 2020

## Slide 2: Introduction
The aim of this presentation is to help all contractors and HAL colleagues understand the process they are required to follow in order to carry out any works within the mothballed building areas in T1.
Baggage will not be covered in this as the ATP process that baggage currently have in place will be the process to follow for any work in a baggage area.
Through this presentation, we will help you to understand the documents and documentation required as well as the systems to use for various types of works that may need to be carried out in the T1 mothballed building - either for decommissioning or for Q6 projects.
We will also help you to understand the governance process in place and the timescales on the authorisation of works. We will help make navigating through the process easier and try to ensure that you are informed in such a way that works will not be held up by the process.

## Slide 3: Index
Site access
Surveying & documentation
Systems & documentation
Job requests & scheduling process explained
Where to send request & the scheduling process explained
How to escalate urgent requests
Tips to expedite the process
Contacts

## Slide 4: Site Access (Green Routes & Red Areas)
The rationale for Site Access procedures is to provide people safe access to the T1 mothballed areas in order to carry out inspections, surveys for work, maintenance inspections or general maintenance.
The Green Route will be in place to provide:
Safe walking routes to access IT and M&E plant rooms and to allow building walk rounds for inspections
Safe access to Red Areas
Access for 3rd party suppliers to carry out maintenance
Controlled access & egress
Areas outside of the Green Routes (Red Areas) will be strictly controlled by Permit to Work. Please also consider that an asbestos permit may be needed for certain works, failure to have this may cause your application to be declined or delayed.
Requirements for securing site access:
Working outside a Green Route will require at least 1 week’s notice
No access to a Red Area will be permitted without a specific permit based on work requirements.
Access to the mothballed areas must be arranged at least 3 days in advance and no access will be granted unless at a minimum you have done the green route induction (this excludes emergency situations).
While the Green Route will be adequately lit to approximately 125 Lux, the Red Areas will be set up by the FM Team as required and the light level will be increased if possible.
If work requirements change while working onsite in a Red Area or if you require access to a Red Area as a result of the work being done, then a new permit will be required through the FM Team.
Emergency access is supported by the FM team, to arrange access in an emergency contact: 079 0953 5674 5674

## Slide 5: Surveying and Documentation
Before any work can be carried out, you will need to understand potential obstacles now that the building has been vacated and the Green Routes are in place. We anticipate two broad categories of work, described below. Under each category we have detailed what will be expected to the best of our knowledge.
General fabric works (including fabric removal works)
To allow a job in this category to proceed we require at a minimum:
a survey of the area the works will take place
a drawing indicating what will be done and where and
detail of the route required to remove rubbish from site.
Minimum supporting documentation will include a full set of RAMS, COSHH date and a list of names of any staff that require access to complete the works. All data and documentation must be submitted with the WAN application at least 1 week before the work is due to take place.
Installation and M&E works (Including asset recovery)
A full survey and drawings will be required of the area the works are planned to take place.
The main difference with this type of work is that you will need to work with the T1 Electrical AP to ensure all DB’s that will be worked on are documented in our standard format (reviewed later in the presentation) and that a full DB schedule is produced even if it is only one circuit that will be affected.
Minimum supporting documentation will include all DB schedules, a full set of RAMS, COSHH date and a list of names of any staff that require access to complete the works. All data and documentation must be submitted with the WAN application at least 1 week before the work is due to take place.

## Slide 6: Systems & Documents
Induction (Mon – Fri 7am – 5pm)
There will be two parts to induction that will take 40 minutes in total, all inductions are to be booked through the FM Team (contact details on the Contacts slide at the end) :
Green Route access induction is for anyone who requires site access for a walk around or visual inspection but does not require access to a Red Area. This induction will cover the Green route Concept, the rules in place for using the Green Routes and general site safety. If a person will not be working in or entering a Red Area then this is the only part of the induction they need to attend.
The second part to the induction will be about working on the site in the Red Areas, what will be required to allow work to take place and what additional equipment will need to be provided (i.e. lighting) to allow for a safe working environment.
WAN System
The WAN system is an airport-wide works request system that covers all work areas in one system (i.e., fire or electrical isolations and RAMS and other documentation). Without a WAN in place, no Red Area work will be allowed to take place and no WAN will be approved until all appropriate documentation is in place and correct. Further information on this system is available on request or on the HUB.
Scheduling
In the next few slides we will explain the scheduling process and purpose in more detail. For any work that could or will have significant impact on this site, the work will have to be entered onto the schedule and will need to secure stakeholder approval before the work can be approved in the WAN system and take place.

## Slide 7: The purpose of the Works Schedule
Why do we need it?
The primary reason for the Works Schedule is to ensure that all M&E and Fabric works that are due to take place in T1 have been reviewed, risk assessed and are being appropriately managed by the right people.
What is it?
The Schedule a management tool that gives T1 stakeholders and APOC clarity around what key activities are taking place at what times.
This gives the stakeholders control over what works can take place at what times in their areas and allows them to feed back any concerns. It also ensures that all mitigating actions are in place should anything go wrong.
Why is it important?
This Schedule allows APOC to have a single point of reference for all works in T1 so that if anything unaccounted for happens during an activity, APOC can see who was working in a particular area at the time. It also provides APOC with a single point of contact for that work.
This means is that in the event of something going wrong, we will be able to react to the situation faster with the right people involved to ensure our roll back plan is implemented as quickly and seamlessly as possible.

## Slide 8: Scheduling Process & time scales
The process below outlines the way in which the schedule is populated and signed off. Any works required to be on the schedule will be approved by Engineering in our scheduling meeting each Monday. These will then be sent for sign off by stakeholders by Wednesday. Once signed off by stakeholders, the work will be scheduled for the following Monday. Note: All works for scheduling should be in no later than 9.30 on Thursday morning.

## Slide 9: Access Process
* please remember to sign in/out at the management office when accessing the site

## Slide 10: Where to send request & the scheduling process explained
The first part of requesting To Do Works in T1 entails going through the WAN process to ensure the correct documentation is in place and that any isolations (i.e. fire, water) are in place. All information submitted through the WAN system will be picked up by the responsible AP’s to sign off the individual sections (i.e. Fire, Water, Electrical).
If the works required in T1 require electrical works, then the DB schedule for this work and all the drawings and documentation should be sent to the Asset Manager and the Safety and Compliance Manager to ensure this work is entered onto the weekly works schedule for the following week while the WAN is processed.
As long as all documentation and WAN is submitted by a contractor no later than 09:30AM on Thursday, the works will take place a week from the following Monday (providing the correct permits are provided alongside the application).
If there are issues with the documentation, DB schedules or additional risk is identified in the Monday sign-off meeting, then the requestor will be notified by either the Asset Manager or the Safety and Compliance Manager of the issues. In most cases, we will do our best to help resolve any issues to push the work forwards but please recognise that risk mitigation is the key reason for having this process.

## Slide 11: How to escalate urgent requests
1. If work is of an urgent nature (excluding emergency repairs), then the requestor should notify The Asset Manager and The Safety and Compliance manager that there is an urgent job request being submitted, this will allow them to plan for the request and help move the request through the process faster.
2. If you require access to attend an emergency repair of your equipment in T1 and are not already on the access system then you can call the FM team on: 07909535674 they will arrange for you to be escorted in on arrival at site.

## Slide 12: Tips to expedite the process
Ensure you are clear on exactly what documentation is required prior to submitting the WAN
Ensure all the required fields and sections on the WAN are filled in correctly
Where electrical work is required ensure a survey of all boards involved has been carried out and a schedule with drawings for each board has been submitted via WAN
If you require full access ensure you have taken the full induction (additional verification / justification may be required for full access, this will be dealt with on an individual basis)
Where a job requires urgent action use the contacts in the Contacts slide to expedite the request

## Slide 13: Contacts
Thank you
FM Team: 079 0953 5674